# CardStack

# Design D3: Task List, Milestones, Timeline, and Effort Matrix

Team: Luke Brogee, Maya Tomarchio     Faculty Advisor: Dr. Aurisano

## Task List

| ID | Task Statement | Module | Owner |
| --- | --- | --- | --- |
| T-01 | Develop checkout_button embed script and domain verification logic. | Checkout Button | Luke |
| T-02 | Design and implement GET /server/v1/button/{id} validation endpoint. | Checkout Button | Luke |
| T-03 | Configure Authentication & User Account service with Google OAuth2 ID token verification. | Authentication & User Account | Maya |
| T-04 | Develop POST /server/v1/auth/google and /logout session management routes. | Authentication & User Account | Maya |
| T-05 | Specify relational schema in Supabase for user, session, and institution_link tables. | Card/Payment Information Store | Maya |
| T-06 | Implement user_card and reward_rule schema with encrypted processor token storage. | Card/Payment Information Store | Maya |
| T-07 | Develop Automatic Card Selection algorithm with scoring and tie-breaking logic. | Transaction & Card Selection Service | Luke |
| T-08 | Specify POST /server/v1/select-card endpoint returning ranked card lists. | Transaction & Card Selection Service | Luke |
| T-09 | Develop Card Processing integration with Payment Processor and idempotency keys. | Card Processing | Luke |
| T-10 | Implement transaction state machine (INITIATED, AUTHENTICATED, PROCESSING, SUCCEEDED, FAILED). | Card Processing | Maya |
| T-11 | Test Financial Institution Setup endpoint /connect-bank-account via Plaid webhooks. | Financial Institution Setup | Maya |
| T-12 | Develop Merchant Webhook sender with exponential backoff and retry queue. | Merchant webhook | Luke |
| T-13 | Implement Transaction History GET /server/v1/transactions paginated endpoint. | Transaction history | Luke |
| T-14 | Design Receipt Forwarding internal queue message handler for automated emails. | Receipt forwarding | Maya |
| T-15 | Develop React Native client screens for the mobile app (wallet, linked cards, card selection). | Mobile app & Web app | Luke |
| T-16 | Develop React Native web portal screens for card management and transaction history. | Mobile app & Web app | Maya |
| T-17 | Validate the end-to-end checkout flow (Checkout Button through Card Processing, Merchant webhook, and Receipt forwarding) with integration tests in the staging sandbox. | Transaction & Card Selection Service / Card Processing | Luke |

## Milestone List

Course deliverables and internal engineering milestones. Course deliverable dates are the dates each was committed to the team repository; implementation dates follow Table 1.

Completed Course Deliverables

- M1 (Completed): High-Level Design (D0) and Initial Scope Approval. Demonstrates system architecture and feasibility through the block diagram and success flow. Date: 10/02/2026 (Week 6). Verified by: Advisor (Dr. Aurisano) review of D0_High_Level_Design.pdf in the repository.

- M2 (Completed): Detailed Design (D1 & D2) with Peer Review. Demonstrates complete API contracts, database schema, and component diagrams. Dates: D1 10/08/2026 (Week 7), D2 10/14/2026 (Week 8), peer review notes 10/21/2026 (Week 9). Verified by: Instructor grading of D1/D2 and peer reviewer feedback recorded in Peer_Review_Notes.md.

Remaining Milestones (chronological; course deliverables and internal engineering milestones)

- M3 – D3 Planning Package (course deliverable, this submission): Task List, Milestones, Timeline, Effort Matrix, WBS, and Risk Register, with Tasklist.md in the repository root and plan sources in /Planning. Date: 10/30/2026 (Week 10). Verified by: Instructor and advisor review of the PDF and repository commit.

- M4 – Data & Sign-In Foundation: Supabase core schema deployed (T-05), Google ID token verification passing unit tests (T-03), checkout button embed renders and validates on a test page (T-01, T-02). Date: 11/20/2026. Verified by: unit test run and live demo at the weekly team meeting; Luke signs off Maya's work and vice versa.

- M5 – Week 14 Progress Report (course deliverable): Reports progress against Tables 1 and 2 and reproduces both tables with actual dates and hours. Date: Week 14 (11/23–11/29/2026). Verified by: Instructor and advisor, against this plan.

- M6 – Fall Foundation Complete: Auth/logout session routes working end to end (T-04) and card selection algorithm passing scoring and tie-break unit tests (T-07). Date: 12/04/2026 (before finals week). Verified by: test report reviewed with advisor at the last fall advisor meeting.

- M7 – Card Store & Selection API: user_card and reward_rule tables live with encrypted tokens (T-06); POST /select-card returns a ranked card list for sample transactions (T-08). Date: 01/22/2027. Verified by: API tests against the staging database; reviewed by both members.

- M8 – Bank Linking & Mobile Alpha: A Plaid sandbox account links and produces a chargeable processor token (T-11); mobile app screens display linked cards and the selected card (T-15). Date: 02/05/2027. Verified by: sandbox demo to advisor; go/no-go decision on the R7 fallback.

- M9 – First Sandbox Payment: A checkout button purchase charges the selected card in the processor sandbox with idempotency keys (T-09); web portal shows linked cards (T-16). Date: 02/19/2027. Verified by: staging sandbox transaction log and recorded demo; Maya verifies.

- M10 – Transaction Lifecycle & History: Transactions move through INITIATED → SUCCEEDED/FAILED correctly (T-10) and appear in the paginated history endpoint (T-13). Date: 03/05/2027. Verified by: state-transition and API tests; Luke verifies.

- M11 – Notifications Complete: Merchant webhooks deliver with exponential backoff and retries (T-12) and receipt emails are sent from the internal queue (T-14). Date: 03/26/2027. Verified by: forced-failure webhook test and received test emails; reviewed with advisor.

- M12 – End-to-End System Validated: Full checkout flow passes integration tests across all modules in the staging sandbox (T-17). Date: 04/09/2027. Verified by: integration test report reviewed by advisor.

- M13 – Final Presentation & Demo: Live demo of the complete CardStack flow and final presentation. Date: 04/20/2027 (confirm against the CS 5002 calendar and expo date). Verified by: course instructor, advisor, and committee.

## Table 1, Timeline

Dates are 2026–27 and follow the UC academic calendar. Each task's end date includes the per-task buffer shown (about 15–20% of its duration), and every milestone is preceded by a protected buffer block (B-rows). The Risk column links schedule-sensitive tasks to the Risk Register.

| ID | Statement / Milestone | Owner | Start | End | Buffer | Deps | Risk |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T-05 | Supabase core schema | Maya | 11/02 | 11/09 | +1 day | None | R4 |
| T-01 | Checkout button embed script | Luke | 11/02 | 11/11 | +2 days | None | — |
| T-03 | Google OAuth verification | Maya | 11/10 | 11/17 | +1 day | T-05 | — |
| T-02 | GET /button/{id} validation | Luke | 11/12 | 11/17 | +1 day | T-01 | — |
| B-M4 | Protected buffer before M4 | All | 11/18 | 11/20 | 3 days | — | R6 |
| T-04 | Auth & logout routes | Maya | 11/21 | 12/02 | +2 days | T-03 | R6 |
| T-07 | Card selection algorithm | Luke | 11/21 | 12/02 | +2 days | T-05 | R6 |
| B-M6 | Protected buffer before M6 | All | 12/03 | 12/04 | 2 days | — | R6 |
| — | Finals week (no planned work) | All | 12/06 | 12/12 | — | — | R6 |
| — | Winter break (catch-up buffer for fall tasks only) | All | 12/13 | 01/10 | Reserve | — | R6 |
| T-06 | Card & reward rule schema | Maya | 01/11 | 01/19 | +1 day | T-05 | R4 |
| T-08 | POST /select-card endpoint | Luke | 01/11 | 01/19 | +1 day | T-04, T-07 | — |
| B-M7 | Protected buffer before M7 | All | 01/20 | 01/22 | 3 days | — | — |
| T-11 | Plaid webhook setup test | Maya | 01/25 | 02/03 | +2 days | T-06 | R1, R7 |
| T-15 | React Native mobile app screens | Luke | 01/25 | 02/03 | +2 days | T-02, T-08 | — |
| B-M8 | Protected buffer before M8 | All | 02/04 | 02/05 | 2 days | — | R7 |
| T-09 | Card Processing integration | Luke | 02/08 | 02/17 | +2 days | T-08, T-11 | R2, R7 |
| T-16 | React Native web portal screens | Maya | 02/08 | 02/17 | +2 days | T-04, T-08 | — |
| B-M9 | Protected buffer before M9 | All | 02/18 | 02/19 | 2 days | — | R2 |
| T-10 | Transaction state machine | Maya | 02/22 | 03/03 | +2 days | T-09 | R2 |
| T-13 | Transaction history API | Luke | 02/22 | 03/03 | +2 days | T-09 | — |
| B-M10 | Protected buffer before M10 | All | 03/04 | 03/05 | 2 days | — | — |
| T-12 | Merchant webhook queue | Luke | 03/08 | 03/24 | +2 days | T-10 | R5, R6 |
| T-14 | Receipt forwarding queue | Maya | 03/08 | 03/24 | +2 days | T-10 | R6 |
| — | Spring break (no planned work) | All | 03/15 | 03/21 | — | — | R6 |
| B-M11 | Protected buffer before M11 | All | 03/25 | 03/26 | 2 days | — | — |
| T-17 | End-to-end integration testing | Luke | 03/29 | 04/07 | +2 days | T-12, T-13, T-14, T-15, T-16 | R2, R5 |
| B-M12 | Protected buffer before M12 | All | 04/08 | 04/09 | 2 days | — | — |
| B-M13 | Demo preparation and fix buffer | All | 04/12 | 04/19 | 6 days | T-17 | R3 |
| M3 | D3 Planning Package (course) | All | — | 10/30 | — | — | — |
| M4 | Data & Sign-In Foundation | All | — | 11/20 | B-M4 | T-01, T-02, T-03, T-05 | — |
| M5 | Week 14 Progress Report (course) | All | — | 11/23–11/29 | — | M4 | — |
| M6 | Fall Foundation Complete | All | — | 12/04 | B-M6 | T-04, T-07 | R6 |
| M7 | Card Store & Selection API | All | — | 01/22 | B-M7 | T-06, T-08 | — |
| M8 | Bank Linking & Mobile Alpha | All | — | 02/05 | B-M8 | T-11, T-15 | R7 |
| M9 | First Sandbox Payment | All | — | 02/19 | B-M9 | T-09, T-16 | R2 |
| M10 | Transaction Lifecycle & History | All | — | 03/05 | B-M10 | T-10, T-13 | — |
| M11 | Notifications Complete | All | — | 03/26 | B-M11 | T-12, T-14 | R5 |
| M12 | End-to-End System Validated | All | — | 04/09 | B-M12 | T-17 | — |
| M13 | Final Presentation & Demo | All | — | 04/20 | B-M13 | M12 | R3 |

## 4. Table 2, Effort Matrix

Estimated effort in hours per task and member. An asterisk (*) marks the member with primary responsibility, who carries the largest share of each task.

| ID | Task | Maya (hrs) | Luke (hrs) | Total (hrs) |
| --- | --- | --- | --- | --- |
| T-01 | Checkout button embed script | 4 | 16* | 20 |
| T-02 | GET /button/{id} validation | 2 | 10* | 12 |
| T-03 | Google OAuth verification | 12* | 2 | 14 |
| T-04 | Auth & logout routes | 12* | 2 | 14 |
| T-05 | Supabase core schema | 10* | 2 | 12 |
| T-06 | Card & reward rule schema | 14* | 4 | 18 |
| T-07 | Card selection algorithm | 6 | 18* | 24 |
| T-08 | POST /select-card endpoint | 2 | 10* | 12 |
| T-09 | Card Processing integration | 8 | 22* | 30 |
| T-10 | Transaction state machine | 14* | 4 | 18 |
| T-11 | Plaid webhook setup test | 16* | 4 | 20 |
| T-12 | Merchant webhook queue | 4 | 14* | 18 |
| T-13 | Transaction history API | 2 | 10* | 12 |
| T-14 | Receipt forwarding queue | 12* | 2 | 14 |
| T-15 | React Native mobile app screens | 4 | 16* | 20 |
| T-16 | React Native web portal screens | 14* | 6 | 20 |
| T-17 | End-to-end integration testing | 8 | 14* | 22 |
| Total |  | 144 (48%) | 156 (52%) | 300 |

Each owner carries most of the hours on their own task; the other member's hours cover code review, pair programming, and testing. Higher-risk tasks (T-07, T-09, T-17) are assigned more support hours.

Balance. The columns are close: Maya 48%, Luke 52%. Splitting the client apps into T-15 (mobile, Luke) and T-16 (web portal, Maya) moved about 20 hours off Luke's column. The remaining gap comes from T-17, which sits with Luke as the team's test owner; to offset it, Maya leads final demo preparation before M13. We will compare actual hours to this matrix at each milestone and reassign work if the gap grows past 10%.

## 5. Work Breakdown Structure

Two-level hierarchy mapping phases to Task List items:

- Phase 1: Frontend & Checkout Integration: T-01 (embed script, Luke), T-02 (button validation, Luke), T-15 (mobile app screens, Luke), T-16 (web portal screens, Maya).

- Phase 2: Authentication & Data Layer: T-03 (Google OAuth, Maya), T-04 (auth routes, Maya), T-05 (Supabase schema, Maya), T-06 (card/reward tables, Maya), T-11 (Plaid setup, Maya).

- Phase 3: Core Business Logic & Card Selection: T-07 (selection algorithm, Luke), T-08 (/select-card endpoint, Luke), T-13 (transaction history, Luke).

- Phase 4: Processing, Webhooks & Notifications: T-09 (card processing, Luke), T-10 (state machine, Maya), T-12 (webhook queue, Luke), T-14 (receipt forwarding, Maya).

- Phase 5: Integration & Delivery: T-17 (end-to-end integration testing, Luke).

## 6. Risk Register

| Risk / Category | Likelihood | Impact | Strategy | Mitigation | Owner | Trigger |
| --- | --- | --- | --- | --- | --- | --- |
| R1: Plaid API Token Limits (External) | Medium | High | Reduce | Use Plaid Sandbox environment extensively; implement mock adapters for integration testing. | Maya | API rate limit errors in staging. |
| R2: Payment Processor Timeouts (Technical) | High | High | Transfer | Rely on idempotency keys (T-09) and reconciliation job to resolve UNKNOWN states (EC-04). | Luke | Processor latency > 5s. |
| R3: Team Member Attrition (Team) | Low | High | Accept | Cross-training across Go backend and React Native frontend; weekly syncs to monitor bottlenecks. | Luke | Missed task deadlines by > 1 week. |
| R4: PCI Compliance Scope (Technical) | Medium | High | Avoid | Strictly enforce token-only storage (D2 Section 2); never store raw PANs in Supabase. | Maya | Security review flagging card data. |
| R5: Merchant Webhook Delivery Failures (External) | Medium | Medium | Reduce | Implement exponential backoff retry queue (T-12) with merchant flagging after N failures. | Luke | HTTP 5xx from merchant endpoint. |
| R6: Academic Calendar Conflicts (Team) | High | Medium | Accept | No tasks scheduled in finals week (12/06–12/12) or spring break (03/15–03/21); winter break held as catch-up buffer for fall tasks; Thanksgiving absorbed in T-04/T-07 buffer. | Luke | Any fall task not complete by 12/04. |
| R7: Plaid Token Not Chargeable (Technical) | Medium | High | Reduce | Prove the Plaid → Stripe processor token path in T-11 before T-09 starts (peer review PR-1); fallback is direct card entry through Stripe Elements. | Maya | T-11 cannot charge a sandbox token by 02/03 (M8). |