## Effort Matrix
Table 2, Effort Matrix — CardStack
Estimated effort in hours. Blue = editable estimates; green highlight = member with primary responsibility (owner).
ID | Task | Owner | Maya (hrs) | Luke (hrs) | Total (hrs) | Owner share
T-01 | Checkout button embed script | Luke | 4 | 16 | 20 | 80%
T-02 | GET /button/{id} validation | Luke | 2 | 10 | 12 | 83.33%
T-03 | Google OAuth verification | Maya | 12 | 2 | 14 | 85.71%
T-04 | Auth & logout routes | Maya | 12 | 2 | 14 | 85.71%
T-05 | Supabase core schema | Maya | 10 | 2 | 12 | 83.33%
T-06 | Card & reward rule schema | Maya | 14 | 4 | 18 | 77.78%
T-07 | Card selection algorithm | Luke | 6 | 18 | 24 | 75%
T-08 | POST /select-card endpoint | Luke | 2 | 10 | 12 | 83.33%
T-09 | Card Processing integration | Luke | 8 | 22 | 30 | 73.33%
T-10 | Transaction state machine | Maya | 14 | 4 | 18 | 77.78%
T-11 | Plaid webhook setup test | Maya | 16 | 4 | 20 | 80%
T-12 | Merchant webhook queue | Luke | 4 | 14 | 18 | 77.78%
T-13 | Transaction history API | Luke | 2 | 10 | 12 | 83.33%
T-14 | Receipt forwarding queue | Maya | 12 | 2 | 14 | 85.71%
T-15 | React Native mobile app screens | Luke | 4 | 16 | 20 | 80%
T-16 | React Native web portal screens | Maya | 14 | 6 | 20 | 70%
T-17 | End-to-end integration testing | Luke | 8 | 14 | 22 | 63.64%
Total |  |  | 144 | 156 | 300
Share of total |  |  | 48% | 52%
Check: owner carries largest share on every row |  |  | OK
Notes
Each owner carries most of the hours on their own task; the other member's hours cover code review, pair programming and testing. Riskier tasks (T-07, T-09, T-17) get more support hours.
Balance: The columns are close (Maya 48%, Luke 52%). Splitting the client apps into T-15 (mobile, Luke) and T-16 (web portal, Maya) moved about 20 hours off Luke's column; the remaining gap comes from T-17, owned by Luke as test owner, offset by Maya leading final demo preparation before M13. We will compare actual hours to this matrix at each milestone and reassign work if the gap grows past 10%.
Hours are draft estimates sized to the Table 1 windows; confirm with each owner (optionally using (O + 4M + P) / 6).